## Slide 1: Capital Works COVID Response CCG Forum April 2020

## Slide 2
Lockdown Level 4
25 March
Routine site inspections:
  Security
  Scaffolding
  Weather tightness
Insurer notified

## Slide 3
Contractual Position
UC | Contractors
Closed campus | Complied with Lockdown and secured sites
EOT supported with costs subject to special conditions within contracts. | Sought UC suspension notice and variation based on change of law provisions in contract
Consider cash flow relief options to enable rapid remobilisation | Contractors make plans to return to site and maintain contact with subs

## Slide 4
Immediate Contractor Concerns
Materials
People
Cash

## Slide 5
MBIE Guidelines to Public Entities
“Without steady cash flow, Contractors will not have the confidence or financial ability to retain their workforce”

## Slide 6
Additional Cost of Delayed Remobilisation
MBIE Guidelines
Potential Mitigations
Forward ordering
Payment in advance
Faster payment cycles
Interim payments
Release of retentions/bonds
For results based contracts, basing payments on previous months

## Slide 7
Principal/Contractor Agreement
MBIE Guidelines
Certainty
Payment terms
Cost recovery principles
Process for remob.
Benefits to supply chain
SOW during lockdown
Daily rate for Level 4
Termination rights
Agreement period

## Slide 8
Planning for Level 3 – Social distancing still in place
Long term viability of Contractors
Period of UC lockdown
Potential for interim works
Product availability

## Slide 9
Conclusion
COVID-19 has consequences for timing and costs on all construction projects.
Joined up thinking is required to manage the risks to all parties.
The outcome will be new ways of working.
This will require leadership and cooperation within organisations and across the sector.